## Sheet1
BLIND VENDOR RENOVATIONS 2014 |  |  |  | as of 3/18/15
PAYMENTS RECORD
| Locations |  |  | Kona Airports | Liliuokalani | Ho`o/#1/Capitol | Kalani/Kee/Kaku | Kona Airports | Ho`o/#1/Capitol | Kalani/Kee/Kaku | Various (Equipment)
| DAGS Job # |  |  | 21-33-7532 | 22-33-7520 | 22-33-7521 | 22-33-7522 | 21-33-7532 | 22-33-7521 | 22-33-7522
| CONTRACT # |  | MOA | 62224 | 62174 | 62597 | 62173 | 63318 | 63286 | 63109 | Award 601
| NAME |  | DAGS | Koa Architects | Lou Chan & Assoc., Inc. | Robt E. Freeburg, AIA | Architects Pacific | Stan's Contractors | Starcom Builders | Brian's Contracting | Mid City Rest.
| ENCUMBRANCE | 852140.3 |  | 32950 | 74735 | 55003 | 40684 | 177950 | 165600 | 240750 | 64468.3
|  | Initial |  | 8/13/13 $25,000 | 7/29/13 $70,000 | 2/6/14 $40,000 | 7/9/13 $40,000 | 9/18/14 $177,950 | 9/10/14 $165,600 | 7/7/14 $225,000 | 9/8/14 $64,468.30
|  | Supp 1 |  | 10/3/14 $7,950 | 10/3/14 $4,735 | 4/9/14 $15,003 | 12/20/13 $684 |  |  | 9/23/14 $15,750
Supp 2
Supp 3
PMT DATE | AWARE AUTH # | PO #
2013-06-17 |  |  | 3000
2014-01-07 | [6 empty] | 9600
2014-01-15 |  |  |  | 2100
2014-02-28 |  |  |  | 700
2014-04-04 | [5 empty] | 12750
2014-05-08 | [5 empty] | 23895
2014-08-20 | 8001661 |  | 12000
2014-08-20 | 8001623 |  |  | 4000
2014-09-09 | 8001969 |  |  | 15350
2014-09-09 | 8001399 |  |  |  |  | 3183
2014-09-15 | 8002123 | [8 empty] | 48450
2014-09-15 | 8002124 | [5 empty] | 25422
2014-11-12 | 8002976 | [8 empty] | 115548
2014-11-26 | 8003124 | [8 empty] | 25875
2014-12-05 | 8003296 | [5 empty] | 1454.31
2014-12-23 | 8003460 | [8 empty] | 38627
2015-01-16 | 8003722 |  |  |  | 29692
2015-01-12 | 8003508 | [7 empty] | 151495
2015-01-27 | 8003918 |  |  |  |  | 8259
2015-03-18 | 8004907 | [8 empty] | 7099
TOTAL PAYMENTS: |  | 538499.31 | 15000 | 22150 | 29692 | 48087 | 36476.31 | 0 | 151495 | 235599 | 0
BALANCE ON CONTRACT: |  |  |  | 10800 | 45043 | 6916 | 4207.69 | 177950 | 14105 | 5151 | 64468.3
AS OF 3/18/15: |  | 328640.99
[9 empty] | Ho`opono | Kalanimoku
Note: Construction at Kona Airport on hold until meeting with contractor in near future. | [8 empty] | 68625 | 82099
Note: Construction contract not awarded for Liliuokalani ($250,000 estimate)
[9 empty] | King Kalakaua | Keelikolani
[9 empty] | 17800 | 75000
[9 empty] | State Capitol | Kakuhihewa
[9 empty] | 67675 | 75000